## Issues Log
Rolling Action Item Log - Customer Support
Revision Dated 20-10-2017
Action Item No. | Open Date | Zodiac Entity | Type of Issue | Description | Priority | Notified By | Status | Action Owner | Due Date | Action to Resolve Issue and/or Status Update | Jet remarks
2017-01 | 2017-01-09 | ZSFR | Processes | JAI request for Payment Terms - 30 days credit. Currently under cash-in-advance. | Med | JAI | On Going | Susheela(ZME) / Rajeev(JAI) | 30th Nov | 6th Feb- Rajeev to send out documents. '23rd Jan 2017 - JAI /Rajeev confirmed the docuemtns are being collected and will soon have it sent out. 19th Jan 2017 - ZME requested proof of payment to send all those units for advance payment has been done. '12th Jan 2017 - Requested for the immediate delivery of parts that have been payed. 'JAI requested spares delivery for those whose payment has been done. 09 Jan 2017'- JAI waspreviously on credit terms , Now ZSFR has put JAI on Cash-in-advance as payment terms. - Several Invoices pending from JAI. Payements cleared.
2017-02 | 2017-01-09 | ZS | Spares | Spares - Open Orders | Med | JAI | Closed | Susheela(ZME) / Matthew (ZSUK) / Cassandra (ZSUS) | 15th Feb 2017 | Action Closed '6th Feb - Updates sent. 16th Jan 2017 - 'ZME updates will be sent on 17 Jan 2017, ZSUS updates will be sent on 18th jan 2017. '12th Jan 2017 - Open Orders Updates have been requested. 09 Jan 2017 -JAI has pending orders from ZSUK , ZSFR , ZSUS & ZPG. JAI would like to have these orders have regular updates & shipped all overdue orders
2017-03 | 2017-01-09 | ZSUS | Spares | Spares -Recline Lock - Annual Order Deffered shipment requested with defered payment ( on credit terms ) | Med | JAI | Closed | Midhun Sajeendran/Cassandra | 24th Jan 2017 | Action Closed 18th Jan - ZSUS agreed ,in coordination with Ammeeta, confirmed the stagered delivery , JAI raised PO. 16th Jan 2017 - ZSUS / Cassandra has acknowledged the stagered delivery and payment terms should be possible , awaiting written confirmation via mail from ZSUS. 09 Jan 2017-Recline Lock PN 849900-409 for B737 5600 seats of ZSUS with a PO Qty 1000ea . JAI requested to have the Qty 1000ea delviered in 3 stages in a period of one year. ( Qty 350 + Qty 350 + Qty300 ) on credit basis for 30 days. ( Approx cost 120K )
2017-04 | 2017-01-09 | ZME | Repair | Repair - Flat rates for Contactors | Med | JAI | Closed | Midhun Sajeendran | 15th Feb 2017 | 16th Jan 2017 - Contactors testing charges converted to Flat rates , charges being finalised. CLosed 12th Jan 2017 - Flat rate proposal under review. 09 Jan 2017-JAI have requeested flat rates for contactors.
2017-04 | 2017-01-17 | ZSUK | Spares | JAI Overpayed Several Orders / ZSUK to provide breakdown & credit these amount. | Med | JAI | closed | Mathew Jones | 15th Feb 2017 | Action Closed 23rd Jan - JAI acknowledged receipt , JAI/Rajeev confirmed to close the action. '19th Jan 2017-Mathew sent spreadhseet detailing the overpayment. Awaiting JAI response. '17th Jan 2017-Mathew to provide a report on the breakdown. '-Previously JAI have issued a number of AOG and critical orders which have been paid against the original overpayment. ZSUK have always obtained JAI's written acceptance prior to processing any demand and we will issue a full report of the over payment ZSUK utilised this money with JAI approval to cover a number of urgent spares and repairs orders and as a result have a sum of £86,546.39 which we would like to return to JAI bank account. Please confirm if we should use the account you previously advised '-JAI made over payments against purchase orders P0389913 and P0481113. In addition , ZSUK were unable to process the bulk of the demand against P0389913 as they were awaiting JAI to instruct us what parts were actually required. '- Approx £89,000.00 which JAI have overpaid against purchase order P0389913
2017-05 | 2017-01-23 | ZME | Spares | Spares -JAI acct on hold - Recline Hydrolock - Urgent request to ship the first batch from Annual Order. | High | JAI | Closed | Maurine/Lorena | 30th Jan 2017 | Action Closed. Qty 50ea Delivered. 26-01-2017 - Released Amount $6000( Qty50 x $120) for recline hydrolock to be shipped from ZSUS. Stock got allocated to other customer meanwhile on priority. Requested to cancel the allocation. Confirmation by Monday. 23-01-2017 - JAI is pleased to have the Annual orde with stagered deliveries and payment, However requires the first batch to be shipped urgently.ZME have informed account is on hold. JAI/Rajeev confirmed 50k out of 100k pending amount will be cleared by end of this week. ZME to release the units ASAP.
2017-06 | 2017-02-06 | ZSUS | Spares | JAI ordered PN 865151-025D & requries Qty2 ea but ZSUS informed MOQ is Qty 150ea. | High | JAI | Closed | Cassandra/Jennifer | 30th Feb 2017 | 6th Feb - ZSUS informed to increase JAI requirements from quantity 2 to 150 pieces or more, or cancel the PO. 865151-025D ordered against order no. P0237216 is required on urgent basis. JAI requries Qty2 ea but ZSUS informed MOQ is Qty 150ea.
2017-07 | 2017-02-06 | ZME | Spares | Spares -JAI acct on hold - Recline Hydrolock - Urgent request to ship second batch. JAI donot want to accept expedite charges. | Med | JAI | Closed | Cassandra/Jennifer | 30th Feb 2017 | Action Closed 13th Feb - Second batch of Qty 300 send. 6th Feb - ZS informed that expedite charges are aplicable to any shipment before the catalogue leadtime. 6th Feb - JAI requested Second batch of recline htydrolock due to operational requirement.
2017-08 | 2017-10-10 | ZSUS | Spares | Invoice Discrepancy -Shipping Invoice donot reflect Order numbers & thereby difficulty in tracking , hence results in payments issues. | Med | JAI | open | Cassandra/Jennifer | 15th Nov | JAI / Rajiv will forward mail to concerned. | The invoice discrepancy documents sent along with the MOM sent on 11.Oct.2017
2017-09 | 2017-10-10 | ZSUS | Spares | BOE discrepancy - JAI strictly informs for any future orders the Custom Invoice / Bill of Entry / Order value all should be aligned & should reflect the same value as the payment goes directly through bank and finance would be held up otherwise. | Med | JAI | open | Cassandra/Jennifer | 15th Nov
2017-10 | 2017-10-10 | ZSUS | Spares | Long Leadtimes + EDD never met. Operations get hindered as units are not received as per promised date | Med | JAI | open | Cassandra/Jennifer | 1st Nov
2017-11 | 2017-10-10 | ZSUS | Spares | Annual Price Escalation are beyond normal computation and not acceptable. Reasons for escalation are not justifiable. | Med | JAI | open | Cassandra/Jennifer | 1st Nov
2017-12 | 2017-10-10 | ZSUS | Spares | ZSUS AOG line is non-responsive. And if a response is provided the CSR lack informative replies ( not solution oriented). | Med | JAI | open | Cassandra/Jennifer | 1st Nov | Jenifer Haney to escalate the matter to management
2017-13 | 2017-10-10 | ZSUS | In-Service | Arm Caps Color variation - ZSUS EY seats of 7070 series has grey leather Armcaps & JAI has noted several variants of grey. | Med | JAI | On Going | Stuart Cho | 26th Oct | Stuart Cho - to confirm the correct variant color
2017-14 | 2017-10-10 | ZSUS | Troubleshooting | PSU Controller used on the ZSUS 7070 Seats supplied by Panasonic, used on Business Class Seats. The Plastic membrane is cracking .Each time this happens JAI is forced to order the NHA which is costing them a lot. Either they want a breakdown or a repair scheme. Membrane P/ 855275-427 & -428 , NUP is $1475 & $2000 respectively. ZSUS To confirm if PSU's in warranty. JAI intends to order Qty 20ea. | Med | JAI | open | Stuart Cho | 1st Nov | JAI/Abhishek to provide details. Stuart Cho to review. | Jetairways Warranty team will be advising on this
2017-15 | 2017-10-10 | ZSUS | In-Service | i) Recline Hydroloks - (Mesag N2-Lok), three major points with regards to this unit- i. Reliability / failing within the 3 year period, ii. MFG & S/N data being erased off the data label, resulting in Warranty claims being declined - Kevin Brannon advised JAI that there was a 3 years Warranty period. iii. Warranty process is expensive for a part that is constantly failing. iv. JAI looking into the warranty aspect of Removal/Installation man-hour + freight charges to be claimed to ZSUS. JAI stated Qty 2000 units have been purchased / replaced within the past 12 months | Med | JAI | On Going | Midhun/Stuart Cho | TBD | 1.We had requested ZSUS if it was technically possible for Midhun to do the inspection/test in the field to validate the warranty per the procedure on the CMM. But this has to be done at the Supplier's site with the right tools hence would not be possible. 2. The warranty period of the unit is 24 months. ( if you have an email from Kevin Brannon that says otherwise , as you stated, do forward it to me ) ACTION: Abhishek - JAI to provide a copy of Kevin's email, they said they still have it. 3. In case that the MFR date is non-readable, the customer can claim the warranty per delivery date of Seats (a/c delivery date to the customer) Work order numbers and pics can be provided to support the removal data. Action: Stuart Cho - Review possibilities apply a clear label over the DATA label to protect the needed information (DOM / S/N) Action: Jennifer Hanney to provide JAI sales data for the Masag N2-LOK over the 12 & 24month period to validate JAI QTY 2000 unit statement. RESPONSE: Jennifer had provided the data. | Please find the attached email
2017-16 | 2017-10-10 | ZSFR | Spares | Cash in Advance -JAI management clearly stated no more Cash in Advance , and credit terms to be adjusted to 30-45 days as due to the several process involved in the documentation. | Med | JAI | open | Farrah | 15th Nov
2017-17 | 2017-10-10 | ZSFR | Spares | Long L/T - JAI shared same concern as ZSUS in terms of Spares deliveries , Long Leadtimes & EDD not met constantly. | Med | JAI | open | Farrah | 30th Nov
2017-18 | 2017-10-10 | ZSFR | Spares | Credit available - JAI informed ZSFR has a credit worth $28K pending & requested to be adjusted against repair orders. | Med | JAI | open | Farrah | 30th Nov |  | This USD 28K should be adjusted by jetairways for the Purchase orders
2017-19 | 2017-10-10 | ZSFR | Spares | BOE discrepancy - JAI strictly informs for any future orders the Custom Invoice / Bill of Entry / Order value all should be aligned & should reflect the same value as the payment goes directly through bank and finance would be held up otherwise | Med | JAI | open | Farrah | 30th Nov
2017-20 | 2017-10-10 | ZSFR | Spares | Monthly SOA - Simple query for SOA is not been able to be provided on time. Several request had to be made. JAI would like to know the direct point of contact in ZSFR. | Med | JAI | open | Farrah | 30th Nov |  | The SOA is still pending
2017-21 | 2017-10-10 | ZSUK | Spares | Open RO’s -Few Open orders with Overdue backlog exist in the repair side. JAI has shared their Open repair order | Med | JAI | open | Paul Ockleford | 26th Oct
2017-22 | 2017-10-10 | ZSUS | Spares | Galley bar Light - Contour Galley on B777 Bar Light P/n D838-05-001 , Bar Light Quotation and ZSUK feedback is not satisfactory. JAI would like to know what is the obsolescence process? Bar Light was manufactured by PAIGE Aero who has gone out of business, UTC have become involved but not willing to provide a solution due to high NRC. | Med | JAI | open | Surjith Matharu | 30th Nov | JAI/Abhishek to provide Galley Top Assy P/N & CMM pages for ZS to discuss with ZSUK Action : Surjith matharu / Katia Smith to review | CMM 25-23-35 R1_C10309-001-_B777 Bar counter sent on 24.Oct.2017
2017-23 | 2017-10-10 | ZS | Repair | Repairs Performance – JAI feels there is a discrepancy in the repair performance graph submitted and what they internally have.We explained the TAT calculation from our end does not include the transit time between the customer and vendor. And have agreed to share the Open RO and discuss with ZS repair team moving forward. | Med | JAI | open | Midhun | 15th Nov
2017-24 | 2017-10-10 | ZS | Repair | Open RO’s - JAI has informed orders open since 2015 & 2016. ZS informed 2015 are not reflecting in ZS orders as they are closed from our end. To discuss and close long pending disputed RO’s. | Med | JAI | open | Midhun | 15th Nov | JAI / Nixon to share the Open RO for ZS to review Action : Midhun to discuss with Repair team to close old pending orders
2017-25 | 2017-10-10 | ZS | Spares | ZOII (C&D )orders L/T – Some orders ( example Latches ) that have been requested has a leadtime for 6 months and not acceptable | Med | JAI | open | Midhun | 15th Nov
2017-26 | 2017-10-10 | ZS | Repair | Reporting Monthly Open Orders - Spares Backlog & Repair Open orders Reports to be pushed out on a regular basis for every operator. A single file containing all info to be shared to the CSM and they filter on each specific airlines and forward onto the corresponding. | Med | JAI | open | Midhun/Walid/Ahmed | 15th Nov
2017-27 | 2017-10-10 | ZS | Repair | Scrap Charges - Nixon ( JAI ) informed scrap charges are high. $429 scrap fee is 50% of NUP and not accepted. ZS to consider waving of scrap fee if a New unit is purchased.( to be discussed with ZS to make it as a standard rule ) | Med | JAI | On Going | Midhun/Walid | 15th Nov
2017-28 | 2017-10-10 | ZS | Processes | Finance – Customer Account & Credit – JAI have outsourced part of their finance process due to the new rules imposed by government since the beginning of the year. This consumes a lot of time. Custom rules are pure electronically controlled and no money can leave the country without being provided goods to that value and the values should match. JAI will not move forward with any more CIA. BOE should match PO value and if value is less declared , that will only be the amount payed. JAI payment terms should be reviewed to make them between 30-45days | Med | JAI | open | Ayman/ Maureen | 30th Nov | – Ayman - to look into the request for JAI to make credit terms to 45 days | Please make a correction in the Description of this point. JAI has not outsourced part of their finance process. Documents related to FOREX remittance needs to be approved by our chartered accountant in view of the new taxation rules and it is advisable to have material in hand before any forex goes out of the country.
2017-29 | 2017-10-10 | ZS | Communications | Monthly SOA - is being sent proactively by Maureen & JAI appreciates the timely data. There is some merit in sending out Monthly SOA to customers. Airlines have the data they need, visibility of all invoices are shown, Missing or Incorrect invoices that are not being paid will be highlighted - Collectively we can work with the customer to resolve any payment issues. | Med | JAI | On Going | Ayman/ Maureen | 26th Oct
2017-30 | 2017-10-10 | ZS | Spares | Spare order to released- JAI had requested to release Spare PN 105021 , PO 279017 | Med | JAI | On Going | Ayman/ Maureen | 26th Oct
2017-31 | 2017-10-10 | ZS | Spares | Spare O2 Masks - Ms Harshala requested to expedite Qty 1000ea O2 masks ordered as they are having critical requirement.O2 masks faced a manufacturing defect on a specific batch and had to be scrapped and now JAI has stock level critical. | Med | JAI | On Going | Midhun/Sibi | 26th Oct | Qty 400 - EDD- immediate shipment requested - ZS Delivered on 14th Sept ( Qty 225 - DHL AWB - 9480321911, Qty 175 - DHL AWB 4788557535) Qty 300 - EDD 28th October - Will be delivered in 2 to 3 working days. AWB will be conveyed by Sibi ( from ZS spares ) Qty 300 - EDD - 28th November ( will be delivered on time ) In addition there was a commercial gesture for these mask orders to place a total of Qty 3000ea , And I have been informed that Qty 2000 has been placed, please do generate the balance Qty 1000ea within the specified time frame. In addition , do share with me the Open Orders for spares , & i can have our team work on the updates.
2017-32 | 2017-10-10 | ZCAE | Warranty | Hot Cup Repair - Warranty Claim - PN : JD025001 W0013417F failure of Hot Jug P/N JD025001 S/N 14219276. This is a BFE item & it was bought by Jet Airways from Sell GMBH in January 2015 under P0365814. The unit has failed in May 2017. This issue was highlighted in AIB SIM. Zodiac denied repair capability when JAI contacted ,& hence hey had to send a number of units in repair to a third party MRO. This has induced additional costs to them they want Zodiac to cover. Jet intends to claim the cost of repair, for three units, from ZCAE as the unit is still under warranty. | Med | JAI | On Going | Midhun/Rutger | 26th Oct | 1. ZCAE has agreed to pay for the invoices. So please share with me the three invoices you have discussed.( to Mano ) 2. Further, ZCAE will contact the relevant people within Jet Airways and Zodiac internally to figure out within what kind of warranty terms these items were sold during the period they were responsible. 3. Finally, ZCAE will set up an agreement with a local MRO with part 145 certification (DGCA approved) to handles these claims in the future. Rutger Van Suchtelen – To contact JAI on this topic & validate the claims.
|  |  |  | There are purchase orders raised in 2015-2016 which were initially released on credit basis and in 2017 Zodiac seats France is asking advance payment for this, As explained in the meeting Jet can not make partial payment for pending parts hence the balance line items to be released on credit basis. The total value of parts pending shipment is Euro 111,771 | [5 empty] | Please find the attached statement of Po awaitng shipment on credit basis

## Look Up Codes
Action Type | Stage
Contract Mgmt | Open
Communications | On Going
Cost | On Hold
PBH | Closed
Processes
Engineering
Spares
Repair
Warranty
Troubleshooting
Forecast
Delivery
In-Service
Retrofit

## Sheet1
shroud zsuk
fading tables
approvcal